## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Candidate Authentication & Session Management | MUST HAVE | Flask / SQLite / OpenCV |  | 1- Not Started
S2 | S2 | US-002 | Face Presence Monitoring | MUST HAVE | OpenCV Haar Cascade |  | 1- Not Started
S2 | S2 | US-003 | Browser Activity & Event Logging | MUST HAVE | SQLite |  | 1- Not Started
S2 | S2 | US-004 | Suspicious Event Detection Engine | MUST HAVE | Rule-based logic |  | 1- Not Started
S3 | S3 | US-005 | Integrity Scoring Module | MUST HAVE | Pandas |  | 1- Not Started
S3 | S3 | US-006 | AI Integrity Report Agent | MUST HAVE | LangChain / LLM |  | 1- Not Started
S3 | S3 | US-007 | Data Science & Analytics Module | MUST HAVE | Pandas / Matplotlib / Seaborn / Scikit-learn |  | 1- Not Started
S3 | S3 | US-008 | Alert & Evidence Management | MUST HAVE | SQLite |  | 1- Not Started
S4 | S4 | US-009 | Examination Monitoring Dashboard | MUST HAVE | Streamlit |  | 1- Not Started
S4 | S4 | US-010 | Reporting & Export Module | MUST HAVE | JSON / CSV |  | 1- Not Started
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Define system architecture & DB schema |  |  |  | Documentation | 1- Not Started
US-001 | 2 | Setup Flask app, SQLite DB & candidate auth |  |  |  | Coding | 1- Not Started
US-001 | 3 | Photo capture (OpenCV) + synthetic data generator |  |  |  | Coding | 1- Not Started
US-001 | 4 | Validate auth & session workflows |  |  |  | Unit Test | 1- Not Started
SPRINT 2 BACKLOG
US-002 | 5 | Face presence monitoring (OpenCV Haar Cascade) |  |  |  | Coding | 1- Not Started
US-003 | 6 | Browser activity & event logging |  |  |  | Coding | 1- Not Started
US-004 | 7 | Suspicious event detection engine |  |  |  | Coding | 1- Not Started
US-002 | 8 | Validate face detection & event logging |  |  |  | Unit Test | 1- Not Started
SPRINT 3 BACKLOG
US-005 | 9 | Build integrity scoring module (Pandas) |  |  |  | Coding | 1- Not Started
US-007 | 10 | Build Data Science analytics module |  |  |  | Coding | 1- Not Started
US-007 | 11 | Validate scoring & analytics outputs |  |  |  | Unit Test | 1- Not Started
US-006 | 12 | Build LangChain AI integrity report agent |  |  |  | Coding | 1- Not Started
US-006 | 13 | Test AI agent across risk scenarios |  |  |  | Unit Test | 1- Not Started
US-008 | 14 | Build alert & evidence management module |  |  |  | Coding | 1- Not Started
US-006 | 15 | Validate AI-generated summaries |  |  |  | Unit Test | 1- Not Started
SPRINT 4 BACKLOG
US-009 | 16 | Build Streamlit monitoring dashboard |  |  |  | Design | 1- Not Started
US-010 | 17 | Implement JSON/CSV export module |  |  |  | Coding | 1- Not Started
US-009 | 18 | End-to-end testing & bug fixes |  |  |  | System Test | 1- Not Started
US-010 | 19 | Prepare documentation & final demo |  |  |  | Documentation | 1- Not Started
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | Week 1 | Finalizing system architecture and database schema took longer than planned | Held a design review session to lock the schema early
2 | Week 3 | OpenCV face detection accuracy varies with lighting conditions | Tuned Haar Cascade parameters and added image preprocessing
3 | Week 5 | Integrating LangChain agent output with integrity score data | Defined a standard JSON schema to pass data between modules
4 | Week 7 | Consolidating all modules into a single Streamlit dashboard | Modularized the dashboard into separate pages per feature

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | Week 1 | Week 2 |  | Documenting assumptions early | Delaying schema decisions | Daily architecture check-ins | Finalized the database schema before coding began
2 | 2 | Week 3 | Week 4 |  | Testing face detection under multiple lighting setups | Assuming default camera settings work everywhere | Logging all detection edge cases | Added a lighting normalization step to the detection pipeline
3 | 3 | Week 5 | Week 6 |  | Reviewing AI-generated summaries for accuracy | Passing unvalidated data to the LangChain agent | Cross-checking scores against event logs | Added a validation step before generating summaries
4 | 4 | Week 7 | Week 8 |  | Running full end-to-end tests before merging | Relying on manual dashboard checks | Modular, page-based dashboard structure | Automated export testing for JSON/CSV outputs
5
6
7